ACADEMIC MIS REVIEW — MONTHLY TEMPLATE

For School / Department / Discipline | Status as on the last day of the preceding month

Purpose: To track current academic targets and activities, actual progress, delays, outcomes and decisions required. Complete one report per School, with discipline/department-level detail attached.

# Instructions: how to fill the form

Complete all reporting particulars below. These identify the reporting unit, month and officer validating the information.

Use one row per measurable indicator or distinct activity. 'Indicator' means the specific item being measured (e.g., classes held, syllabus coverage, pass percentage); 'Target' means the planned number/standard; 'Actual' means what was achieved by the cut-off date.

Where relevant, show both monthly and cumulative figures. State the denominator (e.g., 182 classes held out of 190 scheduled), not just a percentage.

Use a named person and designation for each activity. Avoid entries such as 'department', 'team' or 'concerned faculty' as the only owner.

Mark status as On Track / At Risk / Delayed / Completed / Not Started / On Hold. If delayed or at risk, complete the reason, impact, recovery action, revised date and support required.

Use N/A only where the item genuinely does not apply. Add evidence references, such as report name, meeting minutes, LMS extract or file link. Do not attach unnecessary personal student data.

# A1. Reporting particulars — complete this identification block

| Field | What to enter / example |
| --- | --- |
| School: ______ Department/Discipline: ______ Programme(s): ______ Reporting month: ______ Cut-off date: ______ Dean: ______ HOD/Coordinator: ______ Date submitted: ______ | Enter the name of the School and reporting department/discipline; programme(s) covered; month being reviewed; exact data cut-off date; Dean and HOD/coordinator names; and date the report is submitted. Example: School of Engineering & Technology; Department of Computer Science; B.Tech CSE/BCA; November 2026; status as at 31 October 2026; Dean Dr A; HOD Dr B; submitted 5 November 2026. |

# A2. Executive dashboard — one line per key KPI

| Indicator / KPI | Definition / unit | Annual or semester target | Target for month | Actual this month | Cumulative actual | Variance / status | Brief explanation / action |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Classes delivered | Classes held ÷ classes scheduled | 95% each month | 190 classes | 182/190 (95.8%) | 182/190 | On Track; 8 not held | Make-up classes scheduled for 2–4 Nov. |
| Syllabus coverage | Verified topics completed ÷ planned topics | 100% by 30 Apr | 20% this month | 18% | 42% of semester plan | At Risk; 2 percentage points behind | Two extra tutorials planned; HOD to review weekly. |

Definition: 'Variance' is the difference between target and actual. Explain material gaps, rather than writing only 'less' or 'pending'.

# A3. Activity / task tracker — the core accountability table

| No. | Activity / deliverable | Target / expected output | Planned start | Planned completion | Responsible person (name/designation) | Status & % complete | Progress / evidence | Delay reason / impact | Recovery action & revised date | Benefit / support needed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Use for curriculum revision, lab upgrades, academic events, course-file completion, research milestones, student support initiatives, compliance actions and any other planned task. Example: 'Complete course files for all 8 B.Tech CSE courses'; not 'Course file work'.

# A4. Teaching, learning and curriculum delivery

| Indicator | What to report / unit | Target | Actual this month | Cumulative actual | Gap / reason | Corrective action, owner & date | Evidence reference |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Course files / lesson plans | Courses with approved files ÷ courses offered | 8/8 by 15 Aug | 1 file completed | 7/8 approved | 1 course file pending | Dr X to submit by 28 Oct | Course-file checklist, 25 Oct |
| Practical / lab sessions | Sessions held ÷ sessions scheduled | 40/40 this month | 38/40 | 38/40 | 2 sessions lost due to equipment fault | Lab in-charge to arrange make-up sessions by 31 Oct | Lab timetable / logbook |

# A5. Student attendance, performance and support

| Indicator | Population / denominator | Target | Actual | Gap / students needing support (aggregate) | Action taken | Owner & due date | Outcome / evidence |
| --- | --- | --- | --- | --- | --- | --- | --- |

Examples: average attendance 82% against target 85%; 18 students below the University attendance threshold; 12 students attended remedial sessions; 9 of 12 improved in the next assessment. Report aggregate numbers, not sensitive individual details.

# A6. Assessment and examinations

| Activity / KPI | Target / due date | Actual / completion date | Status | Reason for variance | Pending action / owner | Evidence |
| --- | --- | --- | --- | --- | --- | --- |

Examples: internal assessment completed for 8/8 courses by 20 Oct; marks uploaded for 7/8 courses; one course pending due to evaluator absence, with revised deadline 27 Oct.

# A7. Research, innovation and scholarly activity

| Indicator | Target (year/month) | Actual this month | Cumulative actual | Quality / value / outcome | Next milestone & date | Owner | Evidence |
| --- | --- | --- | --- | --- | --- | --- | --- |

Examples: grant proposals submitted; funding secured; publications accepted/published; patents filed/granted; consultancy; student projects; research seminars. Use the University's approved definitions and do not double-count.

# A8. Faculty, employability, collaborations and student development

| Area / activity | Target | Actual | Variance / explanation | Action / next milestone | Owner & due date | Benefit / evidence |
| --- | --- | --- | --- | --- | --- | --- |

Examples: faculty development completed; faculty vacancies affecting teaching; internships/live projects; industry or academic collaborations with deliverables; student competitions, awards and career-readiness activities.

# A9. Quality assurance, compliance and infrastructure

| Requirement / issue | Applicable standard / target | Due date | Current status | Risk / impact | Action / responsible person | Support / decision required | Evidence |
| --- | --- | --- | --- | --- | --- | --- | --- |

Examples: regulatory submission, accreditation action, audit observation closure, laboratory equipment availability, library/software access, classroom readiness or maintenance affecting teaching.

# A10. Previous review commitments and decisions required

| Previous commitment / issue | Original due date | Current status / evidence | Reason not closed | Next action / revised date | Accountable person | Decision / support required |
| --- | --- | --- | --- | --- | --- | --- |

# A11. Dean’s summary and certification

Key achievements this month (up to 3): __________________________________________

Major gaps / risks and recovery actions: __________________________________________

Decisions/resources required from University leadership: _____________________________

Priorities for next month: _______________________________________________________

Certification: I confirm that the submission has been reviewed with the concerned Heads/Coordinators and is accurate to the best of my knowledge. Evidence is available for verification.

Dean: __________________________  Signature: __________________  Date: ______________